## Copper Interconnect
ADA | DPU_EQUIPMENT_ID | PORT_NUMBER | DCL_ID | CJL ID | DCL Extension Hauled (Y/N) | DCL Extension Name | CIU_ID | CIU Target Support Structure | TLS OJ ID or NBN OJ ID (if used as CIU) | CDS_ID | PCD_ID | SL_ID | Address | CUPID | M_PAIR_ID | COPPER_PATH_STATUS | TLS_CHANGE_DATE | SPECIAL_SERVICES_FLAG | Service Type | Max Length of DPU Extension Cable (m) | Design Cable Length (DPU to Premises) | Cut-In Requirement | Do Not Cut In Reason | Cut-In Status | Comments | Missing CIU and TLS OJ ID | Missing CIU TSS | CIU with multiple TSS | Blank Cut-In Status | Multiple CUPIDs Cut-In at one DPU port | Duplicate CUPID Cut-In to more than one DPU port | Cut-In DPU port with no CUPID | Obsolete LOCs in IWB | IWB LOC not in LOC ID Extract | MDU on hold | SC30 | LOC not in TLS133 file | IWB Issues | CFR Status | Assigned To | Assigned Status | On Hold Comments | Assigned Date | Completion Date | Team Lead
3EAH-02-22 | 3EAH-02-22-DPU-021 | 3 | 3EAH-02-22-DCL-062 | N/A | Y | 3EAH-02-22-DCL-062 | 3EAH-02-22-CIU-062 | 000000000203414789 |  | 3EAH-02-22-CDS-062 | 3EAH-02-22-PCD-062 | LOC000001926892 | ¦¦¦¦¦¦¦31¦GILL¦AV¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-19 | EAHK 5 13 | Disconnect |  | NO |  | 196 | 40 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-021 | 2 | 3EAH-02-03-DCL-080 | N/A | N | N/A | 3EAH-02-03-CIU-080 | 000000000203391678 |  | 3EAH-02-03-CDS-080 | 3EAH-02-03-PCD-080 | LOC000001953917 | ¦¦¦¦¦¦¦69¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P20-O-260 |  | Vacant |  | NO |  | 426 | 15 | Do NOT Cut-In | Vacant Service Type | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-021 | 2 | 3EAH-02-03-DCL-080 | N/A | N | N/A | 3EAH-02-03-CIU-080 | 000000000203391678 |  | 3EAH-02-03-CDS-080 | 3EAH-02-03-PCD-080 | LOC000001953917 | ¦¦¦¦¦¦¦69¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P21-O-187 | EAHK 4 1187 | Disconnect |  | YES |  | 426 | 15 | Do NOT Cut-In | Special Services | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-021 | 2 | 3EAH-02-03-DCL-080 | N/A | N | N/A | 3EAH-02-03-CIU-080 | 000000000203391678 |  | 3EAH-02-03-CDS-080 | 3EAH-02-03-PCD-080 | LOC000001953917 | ¦¦¦¦¦¦¦69¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P7-O-183 |  | Vacant |  | NO |  | 426 | 15 | Do NOT Cut-In | Vacant Service Type | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-021 | 2 | 3EAH-02-03-DCL-080 | N/A | N | N/A | 3EAH-02-03-CIU-080 | 000000000203391678 |  | 3EAH-02-03-CDS-080 | 3EAH-02-03-PCD-080 | LOC000001953917 | ¦¦¦¦¦¦¦69¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-22007 | EAHK 9 124 | Connected |  | NO |  | 426 | 15 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-06 | 3EAH-02-06-DPU-018 | 1 | 3EAH-02-06-DCL-069 | N/A | N | N/A | 3EAH-02-06-CIU-069 | 000000000203681903 |  | 3EAH-02-06-CDS-069 | 3EAH-02-06-PCD-069 | LOC000001990790 | ¦¦¦¦¦¦¦15¦COULSON¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-CA2-B-174 | EAHK 5 314 | Connected |  | N |  | 187 | 14 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-06 | 3EAH-02-06-DPU-008 | 3 | 3EAH-02-06-DCL-031 | N/A | Y | 3EAH-02-06-DCL-031 | 3EAH-02-06-CIU-031 | 000000000203663348 |  | 3EAH-02-06-CDS-031 | 3EAH-02-06-PCD-031 | LOC000002009346 | ¦¦¦¦¦¦¦2¦MILLER¦CT¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-CA2-B-317 | EAHK 5 234 | Connected |  | N |  | 227 | 73 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-013 | 3 | 3EAH-02-03-DCL-049 | N/A | N | N/A | 3EAH-02-03-CIU-049 | 000000000203391916 |  | 3EAH-02-03-CDS-049 | 3EAH-02-03-PCD-049 | LOC000002056127 | ¦¦¦¦¦¦¦55¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-299 | EAHK 9 152 | Disconnect |  | NO |  | 404 | 15 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-033 | 2 | 3EAH-02-03-DCL-128 | N/A | N | N/A | 3EAH-02-03-CIU-128 | 000000000203556829 |  | 3EAH-02-03-CDS-128 | 3EAH-02-03-PCD-128 | LOC000002697123 | ¦¦¦¦¦¦¦26¦CHURCH¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P20-O-21006 | EAHK 2 208 | Disconnect |  | YES |  | 415 | 33 | Do NOT Cut-In | Special Services | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-033 | 2 | 3EAH-02-03-DCL-128 | N/A | N | N/A | 3EAH-02-03-CIU-128 | 000000000203556829 |  | 3EAH-02-03-CDS-128 | 3EAH-02-03-PCD-128 | LOC000002697123 | ¦¦¦¦¦¦¦26¦CHURCH¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-167 | EAHK 9 70 | Disconnect |  | NO |  | 415 | 33 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-015 | 4 | 3EAH-02-03-DCL-058 | N/A | Y | 3EAH-02-03-DCL-058 | 3EAH-02-03-CIU-058 | 000000000203391894 |  | 3EAH-02-03-CDS-058 | 3EAH-02-03-PCD-058 | LOC000002697553 | ¦¦¦¦¦¦¦9¦OAK¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-216 | EAHK 9 113 | Connected |  | N |  | 382 | 40 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-05 | 3EAH-02-05-DPU-006 | 3 | 3EAH-02-05-DCL-023 | N/A | N | N/A | 3EAH-02-05-CIU-023 | 000000000203705371 |  | 3EAH-02-05-CDS-023 | 3EAH-02-05-PCD-023 | LOC000002755634 | ¦¦¦¦¦¦¦30¦CURTAIN¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-166 | EAHK 2 1403 | Connected |  | N |  | 219 | 16 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-007 | 2 | 3EAH-02-21-DCL-025 | N/A | Y | 3EAH-02-21-DCL-025 | 3EAH-02-21-CIU-025 | 3EAH-02-21-PIT-011 |  | 3EAH-02-21-CDS-025 | 3EAH-02-21-PCD-025 | LOC000002864169 | ¦¦¦¦¦¦¦10¦MATHRICK¦ST¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-174 | EAHK 5 121 | Connected |  | N |  | 219 | 75 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-14 | 3EAH-02-14-DPU-026 | 3 | 3EAH-02-14-DCL-099 | N/A | Y | 3EAH-02-14-DCL-099 | 3EAH-02-14-CIU-099 | 000000000203689678 |  | 3EAH-02-14-CDS-099 | 3EAH-02-14-PCD-099 | LOC000002874608 | ¦¦¦¦¦¦¦6¦WALLS¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-56 | EAHK 2 1596 | Connected |  | N |  | 373 | 41 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-06 | 3EAH-02-06-DPU-014 | 2 | 3EAH-02-06-DCL-054 | N/A | N | N/A | 3EAH-02-06-CIU-054 | 000000000203663400 |  | 3EAH-02-06-CDS-054 | 3EAH-02-06-PCD-054 | LOC000002968342 | ¦¦¦¦¦¦¦17¦BILLOLA¦CT¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-CA2-B-80 | EAHK 5 226 | Connected |  | N |  | 240 | 15 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-15 | 3EAH-02-15-DPU-014 | 2 | 3EAH-02-15-DCL-002 | N/A | N | N/A | 3EAH-02-15-CIU-002 | 000000000203414665 |  | 3EAH-02-15-CDS-002 | 3EAH-02-15-PCD-002 | LOC000003556969 | ¦¦¦¦¦¦¦7¦MAGAZINE¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-64 | EAHK 9 49 | Connected |  | N |  | 374 | 22 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-14 | 3EAH-02-14-DPU-001 | 4 | 3EAH-02-14-DCL-004 | N/A | Y | 3EAH-02-14-DCL-004 | 3EAH-02-14-CIU-004 | 000000000203689460 |  | 3EAH-02-14-CDS-004 | 3EAH-02-14-PCD-004 | LOC000003579002 | ¦¦¦¦¦¦¦29¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-271 | EAHK 2 1483 | Connected |  | N | PSTN ONLY | 359 | 106 | Cut-In |  | Did NOT Cut-In | Condition not suitable for cut-in | [13 empty] | Did NOT Cut-In
3EAH-02-22 | 3EAH-02-22-DPU-021 | 3 | 3EAH-02-22-DCL-055 | N/A | Y | 3EAH-02-22-DCL-055 | 3EAH-02-22-CIU-055 | 000000000203414784 |  | 3EAH-02-22-CDS-055 | 3EAH-02-22-PCD-055 | LOC000003629110 | ¦¦¦¦¦¦¦40¦GILL¦AV¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-231 | EAHK 5 160 | Connected |  | N | PSTN ONLY | 187 | 44 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-14 | 3EAH-02-14-DPU-024 | 4 | 3EAH-02-14-DCL-092 | N/A | N | N/A | 3EAH-02-14-CIU-092 | 000000000203691055 |  | 3EAH-02-14-CDS-092 | 3EAH-02-14-PCD-092 | LOC000003658648 | [7 empty] | 382 | 57 | Do NOT Cut-In | Missing CUPID | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-018 | 3 | 3EAH-02-08-DCL-065 | N/A | Y | 3EAH-02-08-DCL-065 | 3EAH-02-08-CIU-065 | 000000000207464107 |  | 3EAH-02-08-CDS-065 | 3EAH-02-08-PCD-065 | LOC000003658682 | ¦¦¦¦¦¦¦55¦EDWARDS¦RD¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-124 | EAHK 5 284 | Connected |  | N |  | 89 | 62 | Restricted Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-010 | 4 | 3EAH-02-08-DCL-038 | N/A | N | N/A | 3EAH-02-08-CIU-038 | 3EAH-02-08-PIT-023 |  | 3EAH-02-08-CDS-038 | 3EAH-02-08-PCD-038 | LOC000003709562 | ¦¦¦¦¦¦¦28¦EDWARDS¦RD¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-112 | EAHK 5 243 | Connected |  | N | PSTN ONLY | 128 | 22 | Restricted Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-05 | 3EAH-02-05-DPU-019 | 3 | 3EAH-02-05-DCL-069 | N/A | N | N/A | 3EAH-02-05-CIU-069 | 000000000203705224 |  | 3EAH-02-05-CDS-069 | 3EAH-02-05-PCD-069 | LOC000003885854 | ¦¦¦¦¦¦¦34¦AVERYS¦RD¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-304 | EAHK 2 1588 | Disconnect |  | N |  | 260 | 74 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-15 | 3EAH-02-15-DPU-013 | 2 | 3EAH-02-15-DCL-005 | N/A | N | N/A | 3EAH-02-15-CIU-005 | 000000000203556884 |  | 3EAH-02-15-CDS-005 | 3EAH-02-15-PCD-005 | LOC000003974088 | ¦¦¦¦¦¦¦15¦MAGAZINE¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-63 | EAHK 9 48 | Disconnect |  | NO |  | 380 | 39 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-15 | 3EAH-02-15-DPU-004 | 4 | 3EAH-02-15-DCL-027 | N/A | Y | 3EAH-02-15-DCL-027 | 3EAH-02-15-CIU-027 | 000000000203557138 |  | 3EAH-02-15-CDS-027 | 3EAH-02-15-PCD-027 | LOC000004283817 | ¦¦¦¦¦¦¦16¦FINCH¦AV¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-32 | EAHK 9 15 | Connected |  | N |  | 361 | 30 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-06 | 3EAH-02-06-DPU-015 | 2 | 3EAH-02-06-DCL-058 | N/A | N | N/A | 3EAH-02-06-CIU-058 | 000000000203663330 |  | 3EAH-02-06-CDS-058 | 3EAH-02-06-PCD-058 | LOC000004345446 | ¦¦¦¦¦¦¦79¦JOBS GULLY¦RD¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P29-O-449 | EAHK 10 194 | Disconnect |  | NO |  | 243 | 57 | Do NOT Cut-In |  | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-06 | 3EAH-02-06-DPU-015 | 2 | 3EAH-02-06-DCL-058 | N/A | Y | 3EAH-02-06-DCL-058 | 3EAH-02-06-CIU-058 | 000000000203663330 |  | 3EAH-02-06-CDS-058 | 3EAH-02-06-PCD-058 | LOC000004345446 | ¦¦¦¦¦¦¦79¦JOBS GULLY¦RD¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-CA2-B-54 | EAHK 5 235 | Connected |  | NO | PSTN ONLY | 243 | 57 | Cut-In |  | Did NOT Cut-In | condition not suitable for cutin | [13 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-008 | 4 | 3EAH-02-08-DCL-031 | N/A | N | N/A | 3EAH-02-08-CIU-031 | 000000001500760540 |  | 3EAH-02-08-CDS-031 | 3EAH-02-08-PCD-031 | LOC000004445239 | ¦¦¦¦¦¦¦3¦ELLIOTT¦CT¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-8 | EAHK 10 807 | Connected |  | N |  | 157 | 38 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-15 | 3EAH-02-15-DPU-001 | 1 | 3EAH-02-15-DCL-012 | N/A | Y | 3EAH-02-15-DCL-012 | 3EAH-02-15-CIU-012 | 3EAH-02-15-PIT-002 |  | 3EAH-02-15-CDS-012 | 3EAH-02-15-PCD-012 | LOC000005009130 | ¦¦¦¦¦¦¦1¦FINCH¦AV¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-6 | EAHK 9 6 | Waiting Connection |  | N |  | 356 | 15 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-06 | 3EAH-02-06-DPU-005 | 1 | 3EAH-02-06-DCL-017 | N/A | N | N/A | 3EAH-02-06-CIU-017 | 000000000203663367 |  | 3EAH-02-06-CDS-017 | 3EAH-02-06-PCD-017 | LOC000005163050 | ¦¦¦¦¦¦¦10¦MILLER¦CT¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-CA2-B-301 | EAHK 5 317 | Connected |  | N |  | 208 | 22 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-017 | 2 | 3EAH-02-21-DCL-053 | N/A | N | N/A | 3EAH-02-21-CIU-053 | 15537718 |  | 3EAH-02-21-CDS-053 | 3EAH-02-21-PCD-053 | LOC000005163176 | [7 empty] | 204 | 41 | Do NOT Cut-In | Missing CUPID | Did NOT Cut-In | [11 empty] | Y |  |  | SC30
3EAH-02-03 | 3EAH-02-03-DPU-009 | 2 | 3EAH-02-03-DCL-033 | N/A | N | N/A | 3EAH-02-03-CIU-033 | 000000001500247759 |  | 3EAH-02-03-CDS-033 | 3EAH-02-03-PCD-033 | LOC000005208697 | ¦¦¦¦¦¦¦33¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-283 | EAHK 9 148 | Connected |  | N | PSTN ONLY | 372 | 15 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-22 | 3EAH-02-22-DPU-026 | 1 | 3EAH-02-22-DCL-071 | N/A | Y | 3EAH-02-22-DCL-071 | 3EAH-02-22-CIU-071 | 000000000203414917 |  | 3EAH-02-22-CDS-071 | 3EAH-02-22-PCD-071 | LOC000005234346 | ¦¦¦¦¦¦¦47¦GILL¦AV¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-22 | EAHK 5 15 | Disconnect |  | N |  | 179 | 57 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-023 | 1 | 3EAH-02-03-DCL-087 | N/A | N | N/A | 3EAH-02-03-CIU-087 | 000000000203391676 |  | 3EAH-02-03-CDS-087 | 3EAH-02-03-PCD-087 | LOC000005246038 | UNIT¦3¦¦¦¦¦¦75¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-230 |  | Vacant |  | NO |  | 430 | 53 | Do NOT Cut-In | Vacant Service Type | Did NOT Cut-In | [11 empty] | Y |  |  | SC30
3EAH-02-03 | 3EAH-02-03-DPU-023 | 2 | 3EAH-02-03-DCL-088 | N/A | N | N/A | 3EAH-02-03-CIU-088 | 000000000203391676 |  | 3EAH-02-03-CDS-088 | 3EAH-02-03-PCD-088 | LOC000005251631 | UNIT¦2¦¦¦¦¦¦75¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-236 | EAHK 9 131 | Connected |  | N |  | 433 | 37 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-023 | 3 | 3EAH-02-03-DCL-089 | N/A | Y | 3EAH-02-03-DCL-089 | 3EAH-02-03-CIU-089 | 000000000203391676 |  | 3EAH-02-03-CDS-089 | 3EAH-02-03-PCD-089 | LOC000005265260 | UNIT¦1¦¦¦¦¦¦75¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-20035 | EAHK 9 130 | Connected |  | N | PSTN ONLY | 433 | 19 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-001 | 2 | 3EAH-02-21-DCL-002 | N/A | Y | 3EAH-02-21-DCL-002 | 3EAH-02-21-CIU-002 | 3EAH-02-21-PIT-013 |  | 3EAH-02-21-CDS-002 | 3EAH-02-21-PCD-002 | LOC000005291901 | ¦¦¦¦¦¦¦47¦NELSON¦ST¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-264 | EAHK 5 165 | Connected |  | N | PSTN ONLY | 230 | 66 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-011 | 3 | 3EAH-02-21-DCL-036 | N/A | N | N/A | 3EAH-02-21-CIU-036 | 000000000203414740 |  | 3EAH-02-21-CDS-036 | 3EAH-02-21-PCD-036 | LOC000005304737 | ¦¦¦¦¦¦¦67¦NELSON¦ST¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-107 | EAHK 5 59 | Connected |  | N |  | 209 | 86 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-023 | 4 | 3EAH-02-03-DCL-090 | N/A | N | N/A | 3EAH-02-03-CIU-090 | 000000000203391847 |  | 3EAH-02-03-CDS-090 | 3EAH-02-03-PCD-090 | LOC000005381348 | [7 empty] | 436 | 37 | Do NOT Cut-In | Missing CUPID | Did NOT Cut-In | [11 empty] | Y |  |  | SC30
3EAH-02-14 | 3EAH-02-14-DPU-015 | 2 | 3EAH-02-14-DCL-054 | N/A | Y | 3EAH-02-14-DCL-054 | 3EAH-02-14-CIU-054 | 000000000203705040 |  | 3EAH-02-14-CDS-054 | 3EAH-02-14-PCD-054 | LOC000006018000 | ¦¦¦¦¦¦¦4¦HICKS¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-26 | EAHK 2 1513 | Connected |  | N | PSTN ONLY | 365 | 51 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-012 | 2 | 3EAH-02-03-DCL-044 | N/A | N | N/A | 3EAH-02-03-CIU-044 | 000000000203391948 |  | 3EAH-02-03-CDS-044 | 3EAH-02-03-PCD-044 | LOC000006040793 | ¦¦¦¦¦¦¦47¦VICTORIA¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-191 | EAHK 9 122 | Connected |  | N |  | 388 | 15 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-003 | 3 | 3EAH-02-03-DCL-009 | N/A | N | N/A | 3EAH-02-03-CIU-009 | 000000000203556735 |  | 3EAH-02-03-CDS-009 | 3EAH-02-03-PCD-009 | LOC000006067185 | ¦¦¦¦¦¦¦13¦CHURCH¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-177 | EAHK 9 28 | Connected |  | N |  | 392 | 31 | Cut-In |  | Did NOT Cut-In | Condition not suitable for cut-in | [13 empty] | Did NOT Cut-In
3EAH-02-22 | 3EAH-02-22-DPU-016 | 4 | 3EAH-02-22-DCL-036 | N/A | Y | 3EAH-02-22-DCL-036 | 3EAH-02-22-CIU-036 | 000000000203414814 |  | 3EAH-02-22-CDS-036 | 3EAH-02-22-PCD-036 | LOC000006073245 | ¦¦¦¦¦¦¦16¦GILL¦AV¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-222 | EAHK 5 149 | Connected |  | N |  | 219 | 40 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-015 | 2 | 3EAH-02-03-DCL-056 | N/A | N | N/A | 3EAH-02-03-CIU-056 | 000000000203391894 |  | 3EAH-02-03-CDS-056 | 3EAH-02-03-PCD-056 | LOC000006103378 | [7 empty] | 377 | 51 | Do NOT Cut-In | Missing CUPID | Did NOT Cut-In | [11 empty] | Y |  |  | SC30
3EAH-02-03 | 3EAH-02-03-DPU-015 | 1 | 3EAH-02-03-DCL-055 | N/A | N | N/A | 3EAH-02-03-CIU-055 | 000000000203391894 |  | 3EAH-02-03-CDS-055 | 3EAH-02-03-PCD-055 | LOC000006130045 | [7 empty] | 377 | 47 | Do NOT Cut-In | Missing CUPID | Did NOT Cut-In | [11 empty] | Y |  |  | SC30
3EAH-02-07 | 3EAH-02-07-DPU-026 | 2 | 3EAH-02-07-DCL-088 | N/A | Y | 3EAH-02-07-DCL-088 | 3EAH-02-07-CIU-088 | 000000001500844839 |  | 3EAH-02-07-CDS-088 | 3EAH-02-07-PCD-088 | LOC000006860590 | ¦¦¦¦¦¦¦68¦AVERYS¦RD¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-CA2-B-272 | EAHK 5 384 | Connected |  | N |  | 165 | 94 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-049 | 1 | 3EAH-02-08-DCL-171 | N/A | N | N/A | 3EAH-02-08-CIU-171 | 000000000203724623 |  | 3EAH-02-08-CDS-171 | 3EAH-02-08-PCD-171 | LOC000006994489 | ¦¦¦¦¦¦¦164¦JOBS GULLY¦RD¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P29-O-435 | EAHK 10 184 | Connected |  | N |  | 36 | 29 | Restricted Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-002 | 3 | 3EAH-02-08-DCL-007 | N/A | Y | 3EAH-02-08-DCL-007 | 3EAH-02-08-CIU-007 | 000000000215249887 |  | 3EAH-02-08-CDS-007 | 3EAH-02-08-PCD-007 | LOC000006999340 | ¦¦¦¦¦¦¦12¦EAGLE¦DR¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-65 | EAHK 5 330 | Connected |  | NO |  | 143 | 35 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-14 | 3EAH-02-14-DPU-004 | 1 | 3EAH-02-14-DCL-013 | N/A | N | N/A | 3EAH-02-14-CIU-013 | 000000000203693177 |  | 3EAH-02-14-CDS-013 | 3EAH-02-14-PCD-013 | LOC000007073476 | ¦¦¦¦¦¦¦6¦GRENFELL¦AV¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-227 | EAHK 2 1489 | Connected |  | N |  | 364 | 14 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-020 | 2 | 3EAH-02-21-DCL-064 | N/A | Y | 3EAH-02-21-DCL-064 | 3EAH-02-21-CIU-064 | 15537718 |  | 3EAH-02-21-CDS-064 | 3EAH-02-21-PCD-064 | LOC000007720437 | ¦¦¦¦¦¦¦9¦HUNTER¦AV¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-112 | EAHK 5 61 | Connected |  | N |  | 197 | 30 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-14 | 3EAH-02-14-DPU-007 | 2 | 3EAH-02-14-DCL-024 | N/A | Y | 3EAH-02-14-DCL-024 | 3EAH-02-14-CIU-024 | 000000000203693312 |  | 3EAH-02-14-CDS-024 | 3EAH-02-14-PCD-024 | LOC000008584972 | ¦¦¦¦¦¦¦24¦GRENFELL¦AV¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-202 | EAHK 2 1472 | Connected |  | N |  | 336 | 27 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-038 | 1 | 3EAH-02-03-DCL-145 | N/A | N | N/A | 3EAH-02-03-CIU-145 | 000000000203391832 |  | 3EAH-02-03-CDS-145 | 3EAH-02-03-PCD-145 | LOC000008603257 | ¦¦¦¦¦¦¦18¦OAK¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P10-O-245 | EAHK 9 138 | Connected |  | N | PSTN ONLY | 390 | 15 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-07 | 3EAH-02-07-DPU-016 | 3 | 3EAH-02-07-DCL-055 | N/A | Y | 3EAH-02-07-DCL-055 | 3EAH-02-07-CIU-055 | 000000000207463850 |  | 3EAH-02-07-CDS-055 | 3EAH-02-07-PCD-055 | LOC000008894584 | ¦¦¦¦¦¦¦47¦AVERYS¦RD¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-CA2-B-288 | EAHK 5 292 | Connected |  | N |  | 191 | 13 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-001 | 2 | 3EAH-02-08-DCL-002 | N/A | Y | 3EAH-02-08-DCL-002 | 3EAH-02-08-CIU-002 | 000000000215249899 |  | 3EAH-02-08-CDS-002 | 3EAH-02-08-PCD-002 | LOC000008923759 | ¦¦¦¦¦¦¦2¦EDWARDS¦RD¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-80 | EAHK 10 917 | Connected |  | N |  | 153 | 20 | Cut-In |  | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-001 | 2 | 3EAH-02-08-DCL-002 | N/A | Y | 3EAH-02-08-DCL-002 | 3EAH-02-08-CIU-002 | 000000000215249899 |  | 3EAH-02-08-CDS-002 | 3EAH-02-08-PCD-002 | LOC000008923759 | ¦¦¦¦¦¦¦2¦EDWARDS¦RD¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-8076 | EAHK 10 917 | Connected |  | N |  | 153 | 20 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-05 | 3EAH-02-05-DPU-021 | 1 | 3EAH-02-05-DCL-075 | N/A | N | N/A | 3EAH-02-05-CIU-075 | 000000000203705455 |  | 3EAH-02-05-CDS-075 | 3EAH-02-05-PCD-075 | LOC000009278296 | ¦¦¦¦¦¦¦44¦AVERYS¦RD¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-346 | EAHK 2 1590 | Connected |  | N |  | 228 | 35 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-021 | 2 | 3EAH-02-08-DCL-075 | N/A | N | N/A | 3EAH-02-08-CIU-075 | 000000015034419693 |  | 3EAH-02-08-CDS-075 | 3EAH-02-08-PCD-075 | LOC000009307512 | ¦¦¦¦¦¦¦37¦EDWARDS¦RD¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-143 | EAHK 5 221 | Connected |  | N |  | 115 | 79 | Restricted Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-14 | 3EAH-02-14-DPU-029 | 3 | 3EAH-02-14-DCL-109 | N/A | Y | 3EAH-02-14-DCL-109 | 3EAH-02-14-CIU-109 | 000000000203690084 |  | 3EAH-02-14-CDS-109 | 3EAH-02-14-PCD-109 | LOC000009811034 | ¦¦¦¦¦¦¦14¦WALLS¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-54 | EAHK 2 1529 | Connected |  | N | PSTN ONLY | 358 | 31 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-22 | 3EAH-02-22-DPU-021 | 3 | 3EAH-02-22-DCL-056 | N/A | Y | 3EAH-02-22-DCL-056 | 3EAH-02-22-CIU-056 | 000000000203414789 |  | 3EAH-02-22-CDS-056 | 3EAH-02-22-PCD-056 | LOC000010109971 | ¦¦¦¦¦¦¦38¦GILL¦AV¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-236 | EAHK 5 180 | Disconnect |  | NO |  | 187 | 39 | Cut-In |  | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-22 | 3EAH-02-22-DPU-021 | 4 | 3EAH-02-22-DCL-056 | N/A | Y | 3EAH-02-22-DCL-056 | 3EAH-02-22-CIU-056 | 000000000203414789 |  | 3EAH-02-22-CDS-056 | 3EAH-02-22-PCD-056 | LOC000010109971 | ¦¦¦¦¦¦¦38¦GILL¦AV¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-236565 | EAHK 5 180 | Disconnect |  | NO |  | 187 | 39 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-025 | 3 | 3EAH-02-21-DCL-073 | N/A | Y | 3EAH-02-21-DCL-073 | 3EAH-02-21-CIU-073 | 000000000203414756 |  | 3EAH-02-21-CDS-073 | 3EAH-02-21-PCD-073 | LOC000010167361 | ¦¦¦¦¦¦¦84¦NELSON¦ST¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-75 | EAHK 5 43 | Connected |  | N | PSTN ONLY | 201 | 28 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-03 | 3EAH-02-03-DPU-024 | 4 | 3EAH-02-03-DCL-094 | N/A | N | N/A | 3EAH-02-03-CIU-094 | 000000000203350168 |  | 3EAH-02-03-CDS-094 | 3EAH-02-03-PCD-094 | LOC000010168280 | [7 empty] | 446 | 42 | Do NOT Cut-In | Missing CUPID | Did NOT Cut-In | [14 empty] | Did NOT Cut-In
3EAH-02-22 | 3EAH-02-22-DPU-025 | 4 | 3EAH-02-22-DCL-078 | N/A | Y | 3EAH-02-22-DCL-078 | 3EAH-02-22-CIU-078 | 000000000203414917 |  | 3EAH-02-22-CDS-078 | 3EAH-02-22-PCD-078 | LOC000010187468 | ¦¦¦¦¦¦¦45¦GILL¦AV¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-26 | EAHK 5 19 | Connected |  | N |  | 179 | 46 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-14 | 3EAH-02-14-DPU-032 | 3 | 3EAH-02-14-DCL-120 | N/A | Y | 3EAH-02-14-DCL-120 | 3EAH-02-14-CIU-120 | 3EAH-02-14-PIT-001 |  | 3EAH-02-14-CDS-120 | 3EAH-02-14-PCD-120 | LOC000010191730 | ¦¦¦¦¦¦¦24¦WALLS¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-58 | EAHK 2 1464 | Disconnect |  | NO |  | 345 | 80 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-002 | 2 | 3EAH-02-21-DCL-006 | N/A | Y | 3EAH-02-21-DCL-006 | 3EAH-02-21-CIU-006 | 000000000203414641 |  | 3EAH-02-21-CDS-006 | 3EAH-02-21-PCD-006 | LOC000010220396 | ¦¦¦¦¦¦¦55¦NELSON¦ST¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-180 | EAHK 5 127 | Disconnect |  | N |  | 219 | 100 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-005 | 2 | 3EAH-02-08-DCL-017 | N/A | N | N/A | 3EAH-02-08-CIU-017 | 000000015030931321 |  | 3EAH-02-08-CDS-017 | 3EAH-02-08-PCD-017 | LOC000010252625 | ¦¦¦¦¦¦¦3¦EAGLE¦DR¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-69 | EAHK 5 323 | Connected |  | N | PSTN ONLY | 141 | 35 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-006 | 1 | 3EAH-02-21-DCL-021 | N/A | Y | 3EAH-02-21-DCL-021 | 3EAH-02-21-CIU-021 | 3EAH-02-21-PIT-011 |  | 3EAH-02-21-CDS-021 | 3EAH-02-21-PCD-021 | LOC000010619896 | ¦¦¦¦¦¦¦8¦MATHRICK¦ST¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-173 | EAHK 5 120 | Connected |  | N |  | 219 | 68 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-14 | 3EAH-02-14-DPU-0032 | 3 | 3EAH-02-14-DCL-120 | N/A | Y | 3EAH-02-14-DCL-120 | 3EAH-02-14-CIU-120 | 3EAH-02-14-PIT-001 |  | 3EAH-02-14-CDS-120 | 3EAH-02-14-PCD-120 | LOC000010191454 | ¦¦¦¦¦¦¦24¦WALLS¦ST¦¦¦EAGLEHAWK¦¦¦VIC¦ | D-EAHK-P26-O-58 | EAHK 2 1464 | Disconnect |  | NO |  | 345 | 80 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-0002 | 2 | 3EAH-02-21-DCL-006 | N/A | Y | 3EAH-02-21-DCL-006 | 3EAH-02-21-CIU-006 | 000000000203414641 |  | 3EAH-02-21-CDS-006 | 3EAH-02-21-PCD-006 | LOC000010226545 | ¦¦¦¦¦¦¦55¦NELSON¦ST¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-180 | EAHK 5 127 | Disconnect |  | N |  | 219 | 100 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-08 | 3EAH-02-08-DPU-0005 | 2 | 3EAH-02-08-DCL-017 | N/A | N | N/A | 3EAH-02-08-CIU-017 | 000000015030931321 |  | 3EAH-02-08-CDS-017 | 3EAH-02-08-PCD-017 | LOC000010265433 | ¦¦¦¦¦¦¦3¦EAGLE¦DR¦¦¦JACKASS FLAT¦¦¦VIC¦ | D-EAHK-P31-O-69 | EAHK 5 323 | Connected |  | N | PSTN ONLY | 141 | 35 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In
3EAH-02-21 | 3EAH-02-21-DPU-0006 | 1 | 3EAH-02-21-DCL-021 | N/A | Y | 3EAH-02-21-DCL-021 | 3EAH-02-21-CIU-021 | 3EAH-02-21-PIT-011 |  | 3EAH-02-21-CDS-021 | 3EAH-02-21-PCD-021 | LOC000010687654 | ¦¦¦¦¦¦¦8¦MATHRICK¦ST¦¦¦CALIFORNIA GULLY¦¦¦VIC¦ | D-EAHK-P27-O-173 | EAHK 5 120 | Connected |  | N |  | 219 | 68 | Cut-In |  | Physical and Logical Cut-In Complete | [14 empty] | Did NOT Cut-In

## vamsi1
LOC | CPI | CUPID
LOC000001953917 | CPI300006806073 | D-EAHK-P27-O-100
LOC000001990790 | CPI300006806239 | D-EAHK-P31-O-8
LOC000002009346 | CPI300006806040 | D-EAHK-P27-O-117
LOC000002697553 | CPI300006806485 | D-EAHK-CA2-B-590
LOC000002755634 | CPI300006805952 | CSLL-ORD-001
LOC000002864169 | CPI300006806646 | D-EAHK-CA2-B-74
LOC000002874608 | CPI300006805962 | CSLL-ORD-001
LOC000002968342 | CPI300006805885 | D-EAHK-CA2-B-289
LOC000003556969 | CPI300006805782
LOC000003579002 | CPI300006806094
LOC000003629110 | CPI300006806429
LOC000003658648 | CPI300006805806 | CSLL-ORD-001
LOC000003658682 | CPI300006806237 | D-EAHK-P31-O-74
LOC000003709562 | CPI300006805776 | D-EAHK-CA2-B-303
LOC000003885854 | CPI300006805958 | D-EAHK-CA2-B-177
LOC000004283817 | CPI300006806029
LOC000004345446 | CPI300006806472 | D-EAHK-P10-O-297
LOC000004445239 | CPI300006806271
LOC000005163050 | CPI300006806371 | D-EAHK-P10-O-273
LOC000005208697 | CPI300006806427 | D-EAHK-P26-O-240
LOC000005251631 | CPI300006806351
LOC000005265260 | CPI300006805904 | CSLL-ORD-001
LOC000005291901 | CPI300006806188 | D-EAHK-P27-O-163
LOC000005304737 | CPI300006806018 | CSLL-ORD-001
LOC000006018000 | CPI300006806394 | D-EAHK-P10-O-3
LOC000006040793 | CPI300006806123 | D-EAHK-P10-O-34
LOC000006067185 | CPI300006806583
LOC000006073245 | CPI300006805809 | CSLL-ORD-001
LOC000006860590 | CPI300006806458 | D-EAHK-P27-O-38
LOC000006999340 | CPI300006806030 | CSLL-ORD-001
LOC000007073476 | CPI300006806433 | D-EAHK-CA2-B-503
LOC000007720437 | CPI300006805907
LOC000008584972 | CPI300006806105
LOC000008603257 | CPI300006806366 | CSLL-ORD-001
LOC000008894584 | CPI300006806473 | D-EAHK-CA2-B-221
LOC000008923759 | CPI300006806135 | D-EAHK-P27-O-84
LOC000009278296 | CPI300006806452
LOC000009811034 | CPI300006806007 | D-EAHK-P27-O-101
LOC000010167361 | CPI300006805780
LOC000010168280 | CPI300006806498 | D-EAHK-P31-O-81
LOC000010187468 | CPI300006806411 | CSLL-ORD-001
LOC000010252625 | CPI300006805773
LOC000010619896 | CPI300006805794
LOC000010187468 | CPI3000068068788411 | CSLL-ORD-0016
LOC000009811034 | CPI30000680698987 | D-EAHK-P27-O-10166
LOC000002697123 | CPI30000680698987 | D-EAHK-P20-O-21006
LOC000002697123 | CPI30000680698987 | D-EAHK-P10-O-167